## Bug Report Template
Module | Type | FE/BE | Description | Status | Build _2 _Status | Severity | Priority | Assignee | Reporter | Platform | Component | Labels | Parent | Attachments | Sprint | StoryPoints | DueDate | StartDate | TeamOrProd
Dashboard | Bug |  | It should be all location instead of location | Open
Dashboard | Bug |  | In 2024 overview, cards are not properly aligned text is going out of the box | Open
Dashboard | Bug |  | It should be only Overview, not 2024 Overview | Open
Dashboard | Bug |  | It should be only Overview, not 2024 Overview | Open
Dashboard | Bug |  | View Task is not working | Open